## Slide 1: WACTE
Strategic Planning October 25, 2017

## Slide 2: WACTE Strategic Planning
  Work to Date:
    2007 Current Strategic Plan Adopted
    June 2016: Executive Board discussion/work to
            condense 7 goals to 4
    October 2016: WACTE - SWOT Analyses
    January 2017: Summary of SWOT Chart/discussion
    April 2017: Work delayed to October 2017

## Slide 3: WACTE Strategic Planning
    Upcoming Work:
      October 2017: Determination of Common Threads / Establish goals for Common Threads
      January 2018: Establish Action Items to reach goals
      January-April 2018: Executive Board/Deans/Directors draft final Strategic Plan
      April 2018: WACTE adoption 2018 Strategic Plan

## Slide 4: WACTE Strategic Planning
Work for today:
Determine Common Threads (Table Groups): 45 minutes
    10 minutes Review SWOT Analyses handout……
    15 minutes Review draft Common Threads: edit/revise/change/develop new
    20 minutes Group Report Out

## Slide 5: WACTE Strategic Planning
Work for today:
Establish Goals for Threads (Table Groups): 45 minutes
    25 minutes Determine 1-2 goals per Thread
    20 minutes Group Report Out

## Slide 6: WACTE Strategic Planning
WHEW!!!
Thank you for all your work!